## Sheet1
CASL Online Education and Approval Qualification System
Activity |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Feasibility Study | bar: 1
Prepare work plan | bar: 1
Identify problems on the current system | bar: 2
Identify requirements | bar: 2
Design database and system architecture | bar: 3 to 4
Program design and UI design | bar: 3 to 10
Program Writing | bar: 7 to 14
System Testing | bar: 7 to 14
Debugging | bar: 7 to 14
Produce User Documentation
Prepare for demonstration
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Time(Week)
CASL Online Education and Approval Qualification System
| Activity |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Feasibility Study | bar: 1
Prepare work plan | bar: 1
Identify problems on the current system | bar: 2
Identify requirements | bar: 2
Design database and system architecture | bar: 3 to 4
Program design and UI design | bar: 3 to 10
Program Writing | bar: 7 to 13
System Testing | bar: 7 to 13
Debugging | bar: 7 to 13
Produce User Documentation
Prepare for demonstration
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Time(Week)
Mini Games Application
| Activity |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Feasibility Study | bar: 1 to 5
Prepare work plan | bar: 1 to 5
Identify Functions | bar: 1 to 5
Design database | bar: 6 to 8
Application design and UI design | bar: 6 to 10
Application implementation | bar: 7 to 12
Application Testing | bar: 7 to 12
Debugging | bar: 7 to 12
Produce User Documentation | bar: 4 to 12
Prepare for demonstration | bar: 11 to 13
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Time(Week)